## Summary
Test Execution Report - 1st Energy Rebate (1ER)
Execution Date: 2026-08-20 ¦ Tested By: Claude (automated - Playwright) ¦ App: https://1er.softwareco.com
Source sheet | 1st_Energy_Rebate_TestCases (2).xlsx - 74 test cases total
Test cases attempted this session | 44 (rows 2-45 of the source sheet)
Not yet executed | Rows 46-75 (~29 cases) - session stopped before completion
Results breakdown
Pass | 12
Needs Review | 1
N/A | 2
Inconclusive | 2
Not Fully Verified | 5
Partially Verified | 1
Not Tested | 17
Fail | 2
Not Verified | 1
Not Implemented | 1
CRITICAL FINDING | Jobs list ("All Jobs" page) never loads job data - see "Critical Findings" sheet
Login used | johns@softwareco.com / admin@123

## Critical Findings
Title | Severity | Description | Evidence | Impact | Recommendation
Jobs list never loads any data ("No Data Found" always shown) | Critical / Showstopper | The "All Jobs" page (/jobs) fetches data for all 4 filter dropdowns (Company, Status, Contractor Group, Auditor) on load, but never calls any endpoint to fetch the actual job records. Confirmed via network trace: 11 API calls fire on page load, none resembling a job-list/search endpoint, even after an 8-second wait. Table always renders "No Data Found" regardless of real data existing. | Reproduced with a completely fresh login -> single navigation to /jobs (no prior navigation/state). This morning (same session, same account) the same page showed real jobs (M8200003, M8200002, "Test Job 5", etc.) - something changed between then and now. | Blocks verification of ~10 test cases in this sheet that depend on existing job records (Contractor Group filter results, phone-edit behavior, VBS/CES indicators, Resend SMS label, Customer Signature UI, task selection, photo download, job info field layout, Add Product step gating). | Check recent deploys/commits touching the Jobs list data-fetch call. Given filter dropdowns still populate correctly, this looks like a missing or broken call to the job-list endpoint specifically, not a full outage.

## Test Cases
Test ID | Source Row | Test Case Title | Status | Actual Result | Notes | Executed By | Date
TC-01 | 2 | Login screen UI displays correctly without overlapping fields | Pass | No overlapping fields observed; Email ID, Password, and Log In button are cleanly spaced. |  | Claude (automated - Playwright) | 2026-08-20
TC-02 | 3 | Duplicate error message is not shown twice on invalid login | Needs Review | "Invalid credentials" appears TWICE simultaneously: once as a top-right toast notification, once as a persistent inline banner in the form. | Could be the reported duplicate-message bug, or an intentional toast+inline UX pattern - needs human judgment call. | Claude (automated - Playwright) | 2026-08-20
TC-03 | 4 | Correct validation message when signing in with blank phone number | N/A | This app's login screen only offers Email ID / Password - there is no "sign in with phone number" tab/option to test. |  | Claude (automated - Playwright) | 2026-08-20
TC-04 | 5 | Password show/hide (eye) icon is disabled when password field is empty | Inconclusive | Automated click on the icon did not toggle the password field's type attribute in either the empty or filled state. | The locator used to find the icon may not have targeted the exact clickable element - needs manual verification. | Claude (automated - Playwright) | 2026-08-20
TC-05 | 6 | Company name persists in filter after clicking TOTAL JOB CREATED tile | Not Fully Verified | Confirmed the Company filter dropdown exists on Dashboard; did not complete the full select-company -> click-tile -> verify-persistence flow. |  | Claude (automated - Playwright) | 2026-08-20
TC-06 | 7 | Resetting global date filter clears date in Job Tracking section | Not Fully Verified | Confirmed the date filter exists; reset behavior not exercised. |  | Claude (automated - Playwright) | 2026-08-20
TC-07 | 8 | All Dashboard sections respect the applied global date filter | Not Fully Verified | Average Job Completion Time widget and Job Tracking chart confirmed present; synchronized update across sections not verified. |  | Claude (automated - Playwright) | 2026-08-20
TC-08 | 9 | DAYS value displays for all companies in Average Job Completion Time widget | Partially Verified | Widget shows "6.68 Days" with no company filter applied; not tested against multiple specific companies individually. |  | Claude (automated - Playwright) | 2026-08-20
TC-09 | 10 | Dashboard sections do not flash unrelated data while loading after redirect | Not Tested | Requires network throttling to reliably observe the loading transition; not attempted. |  | Claude (automated - Playwright) | 2026-08-20
TC-10 | 11 | Redirecting from a specific Dashboard tile opens the correct filtered section | Fail | Clicking the "Total Jobs Being Assessed" dashboard tile redirects to /jobs with the "All" tab selected and Status filter unset - NOT pre-filtered to "Being Assessed" as expected. | Confirmed via screenshot: sidebar shows "All" highlighted, Status dropdown shows default "Select Status". | Claude (automated - Playwright) | 2026-08-20
TC-11 | 12 | Search text and results persist after viewing notes and returning to Jobs list | Not Fully Verified | Search for "Test" returned 1 matching row, but no accessible "view" action was found on that row to complete the Notes navigation step. | Also affected by the Jobs-list data bug (see Critical Findings). | Claude (automated - Playwright) | 2026-08-20
TC-12 | 13 | Dashboard does not show a blank screen when redirected from the Rebate section | Pass | Dashboard loaded correctly with full content after navigating from Rebate section; body text was not blank. |  | Claude (automated - Playwright) | 2026-08-20
TC-13 | 14 | Rebate action title does not show "NA" when company name is missing | Pass | No literal "NA" text found on the Rebate page. | Only confirms absence in current data - could not confirm the specific no-company-name scenario exists to fully validate. | Claude (automated - Playwright) | 2026-08-20
TC-14 | 15 | Chart tooltip/slot is visible on hover across all data points | Not Verified | No matching chart element found via the selector used (recharts/canvas class patterns); Dashboard may render charts differently. |  | Claude (automated - Playwright) | 2026-08-20
TC-15 | 16 | Logout button in Profile is visually enabled and clearly actionable | Pass | No dedicated Profile page exists - account info + Logout live in the avatar dropdown. Logout button has opacity 1 / pointer-events auto (visually enabled) and, after confirming the "Are you sure?" modal, correctly logs the user out and redirects to /log-in. |  | Claude (automated - Playwright) | 2026-08-20
TC-16 | 17 | Long CSV file name is truncated/wrapped properly in Update Job screen | Not Tested | Blocked by needing an existing job to update, compounded by the Jobs-list data bug. |  | Claude (automated - Playwright) | 2026-08-20
TC-17 | 18 | Job upload is blocked when no document/file is selected | Pass | The Upload button is visually disabled (greyed out, muted color vs. the app's normal dark-blue enabled style) until App Version and a file are both provided - cannot be clicked to submit without them. | Prevention via disabled button rather than a post-click error message - arguably better UX, satisfies the test intent. | Claude (automated - Playwright) | 2026-08-20
TC-18 | 19 | A confirmation tooltip appears when copying a job option | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-19 | 20 | Clear button alignment and T&C field are functional in job view | Not Tested | Blocked by the Jobs-list data bug (no job available to open). |  | Claude (automated - Playwright) | 2026-08-20
TC-20 | 21 | Installer screen loads correctly instead of a blank grey screen | Pass | Installer list page loads with header, filters, and table structure; page body text length 893 chars, not blank. |  | Claude (automated - Playwright) | 2026-08-20
TC-21 | 22 | Date range can be selected correctly when generating a project report | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-22 | 23 | Required fields on the Installer screen show an asterisk indicator | Pass | 6 required fields correctly show a red asterisk on the Add Installer form (after waiting for skeleton loaders to clear). | Initial check gave a false "0 asterisks" result due to screenshotting before the form finished loading - corrected on retest. | Claude (automated - Playwright) | 2026-08-20
TC-23 | 24 | Success message is shown after uploading installer logo/image | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-24 | 25 | Company name does not show "undefined" when switching company from Installer/Rebate | Pass | 0 instances of "undefined" text found immediately after switching from Installer to Rebates. |  | Claude (automated - Playwright) | 2026-08-20
TC-25 | 26 | Company logo displays correctly after signing in with a new company | N/A | No newly onboarded/unused company account was available to test with. |  | Claude (automated - Playwright) | 2026-08-20
TC-26 | 27 | Week labels on charts are fully visible and not cut off | Not Fully Verified | Dashboard screenshot captured but the chart's X-axis / week-label area fell below the captured viewport. |  | Claude (automated - Playwright) | 2026-08-20
TC-27 | 28 | Editing business name does not repeatedly reopen an unintended popup | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-28 | 29 | An empty-state message is shown instead of blank space when Installer has no records | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-29 | 30 | Validation messages reference the correct field name | Pass | Empty Add Job submit produced specific, correctly-named messages: "Customer Type is required", "Scheme is required", "Cost (inc GST) of new unit is required", "Company Name is required". |  | Claude (automated - Playwright) | 2026-08-20
TC-30 | 31 | Numeric fields reject negative amounts on Create Job screen | Pass | Typing "-100" into the Product Price field results in a field value of "100" - the minus sign is stripped/rejected at input level. |  | Claude (automated - Playwright) | 2026-08-20
TC-31 | 32 | Required-field validation only triggers on Save/Next, not prematurely | Pass | 0 validation errors shown after focusing then blurring a required field, before clicking Next. |  | Claude (automated - Playwright) | 2026-08-20
TC-32 | 33 | Chat search returns results for inactive users too | Not Tested | No known inactive user with an existing chat thread was available to test with. |  | Claude (automated - Playwright) | 2026-08-20
TC-33 | 34 | Phone number field does not prepend an extra "0" on repeated job edits | Not Tested | Blocked by the Jobs-list data bug (no existing job available to repeatedly edit). |  | Claude (automated - Playwright) | 2026-08-20
TC-34 | 35 | VBS/CES status indicators do not blink/show as completed prematurely | Inconclusive | Could not observe live status-indicator behavior since the Jobs list shows no data at all. | Blocked by the Jobs-list data bug. | Claude (automated - Playwright) | 2026-08-20
TC-35 | 36 | Resend SMS label displays correctly instead of "undefined" in Customer Signature view | Not Tested | Blocked by the Jobs-list data bug (no job with a pending signature available). |  | Claude (automated - Playwright) | 2026-08-20
TC-36 | 37 | Customer Signature button does not overlap its container border | Not Tested | Blocked by the Jobs-list data bug. |  | Claude (automated - Playwright) | 2026-08-20
TC-37 | 38 | Task options can be selected when adding a task to a job | Not Tested | Blocked by the Jobs-list data bug (no existing job to add a task to). |  | Claude (automated - Playwright) | 2026-08-20
TC-38 | 39 | Images render without an unintended dotted/placeholder pattern | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-39 | 40 | Download button works for job photos | Not Tested | Blocked by the Jobs-list data bug. |  | Claude (automated - Playwright) | 2026-08-20
TC-40 | 41 | Job information fields display complete left-side border without clipping | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-41 | 42 | Clicking the date icon opens the date picker on the date filter | Pass | Date picker becomes visible immediately after clicking the Dashboard's "Select Date Range" field. |  | Claude (automated - Playwright) | 2026-08-20
TC-42 | 43 | Total record count is displayed when "All Jobs" is selected | Not Implemented | No "Total Records" indicator found on the All Jobs page. | This row is tagged "Suggestion" in the source sheet, not a hard requirement - treat as a feature request, not a defect. | Claude (automated - Playwright) | 2026-08-20
TC-43 | 44 | Add Product is only available at the correct step of job creation | Not Tested |  |  | Claude (automated - Playwright) | 2026-08-20
TC-44 | 45 | Job records remain filtered by selected status after switching module | Fail | Selected Status filter "Good to Go" on All Jobs, navigated to Dashboard and back to Jobs - filter reset to default "Select Status" instead of persisting. |  | Claude (automated - Playwright) | 2026-08-20

## Not Executed
Source rows | 46-75
Reason | Batch 4 (rows 46-65: Contractor Group dropdown behavior, keyboard navigation, guided tour, Workspace double-click, plus row 63-65) was started but stopped mid-run at the user's request before completion. Rows 55-62 and most of 66-75 are Android/Mobile-app-only test cases that cannot be executed via browser automation - no mobile device/emulator is available in this environment.